## Resource Allocation
Behind the Seens — Resource Allocation & Monthly Cost Plan
Project Managers: Ezz El-Din, Ibrahim, Ahmed, Mariam, Arwa, Hoor ¦ Sponsor: NTI – Digital Egypt Youth Initiative ¦ Duration: Aug 2026 – Feb 2028 (18 months)
Resource / Task | Team / Workstream | Rate / Basis (EGP) | Active Months | Cost (EGP) | M1 Aug-26 | M2 Sep-26 | M3 Oct-26 | M4 Nov-26 | M5 Dec-26 | M6 Jan-27 | M7 Feb-27 | M8 Mar-27 | M9 Apr-27 | M10 May-27 | M11 Jun-27 | M12 Jul-27 | M13 Aug-27 | M14 Sep-27 | M15 Oct-27 | M16 Nov-27 | M17 Dec-27 | M18 Jan/Feb-28
Data Engineer | Data & Research | 12000 | 18 | 216000 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
T2.1 Data collection & sourcing |  |  | Oct-26, Nov-26 |  |  |  | ● | ●
T2.2 Data cleaning & annotation |  |  | Nov-26, Dec-26 |  |  |  |  | ● | ●
T6.1 Bug fixing & polish |  |  | Dec-27, Jan/Feb-28 | [17 empty] | ● | ●
T6.4 MVP launch & handover |  |  | Jan/Feb-28 | [18 empty] | ●
UX/UI Designer | Design & Experience | 12000 | 18 | 216000 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
T2.4 UX/UI research & wireframes |  |  | Oct-26, Nov-26 |  |  |  | ● | ●
T4.3 Expert Review Dashboard |  |  | Jun-27, Jul-27 | [11 empty] | ● | ●
T6.1 Bug fixing & polish |  |  | Dec-27, Jan/Feb-28 | [17 empty] | ● | ●
T6.4 MVP launch & handover |  |  | Jan/Feb-28 | [18 empty] | ●
Clinical Advisory Committee (3 full-time) | Clinical | 60000 | 18 | 1080000 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
T2.3 Define ASD indicator criteria |  |  | Dec-26, Jan-27 | [5 empty] | ● | ●
T5.1 Validation dataset & protocol |  |  | Sep-27 | [14 empty] | ●
T5.3 UAT — Parents & Therapists |  |  | Oct-27, Nov-27 | [15 empty] | ● | ●
T5.4 Clinical sign-off |  |  | Nov-27, Dec-27 | [16 empty] | ● | ●
T6.4 MVP launch & handover |  |  | Jan/Feb-28 | [18 empty] | ●
AI Engineer (3 specialists) | AI/ML Development | 45000 | 18 | 810000 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
T2.3 Define ASD indicator criteria |  |  | Dec-26, Jan-27 | [5 empty] | ● | ●
T3.1 CV feature extraction |  |  | Feb-27, Mar-27 | [7 empty] | ● | ●
T3.2 VLM semantic extraction |  |  | Feb-27, Mar-27 | [7 empty] | ● | ●
T3.3 Ensemble classification model |  |  | Apr-27, May-27 | [9 empty] | ● | ●
T3.4 LLM fine-tuning for reports |  |  | Mar-27, Apr-27 | [8 empty] | ● | ●
T4.4 RAG chatbot integration |  |  | Jul-27, Aug-27 | [12 empty] | ● | ●
T6.1 Bug fixing & polish |  |  | Dec-27, Jan/Feb-28 | [17 empty] | ● | ●
T6.4 MVP launch & handover |  |  | Jan/Feb-28 | [18 empty] | ●
Full-stack Developer | Platform Engineering | 12000 | 18 | 216000 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
T4.1 Backend API development |  |  | Jun-27, Jul-27 | [11 empty] | ● | ●
T4.3 Expert Review Dashboard |  |  | Jun-27, Jul-27 | [11 empty] | ● | ●
T4.4 RAG chatbot integration |  |  | Jul-27, Aug-27 | [12 empty] | ● | ●
T4.5 Connect pipeline to applications |  |  | Aug-27, Sep-27 | [13 empty] | ● | ●
T6.1 Bug fixing & polish |  |  | Dec-27, Jan/Feb-28 | [17 empty] | ● | ●
T6.4 MVP launch & handover |  |  | Jan/Feb-28 | [18 empty] | ●
Mobile Developer | Platform Engineering | 12000 | 18 | 216000 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
T4.2 Mobile app build |  |  | Jun-27, Jul-27, Aug-27 | [11 empty] | ● | ● | ●
T6.1 Bug fixing & polish |  |  | Dec-27, Jan/Feb-28 | [17 empty] | ● | ●
T6.4 MVP launch & handover |  |  | Jan/Feb-28 | [18 empty] | ●
QA Engineer | Quality Assurance | 12000 | 18 | 216000 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
T5.2 Accuracy/reliability testing |  |  | Sep-27, Oct-27 | [14 empty] | ● | ●
T5.3 UAT — Parents & Therapists |  |  | Oct-27, Nov-27 | [15 empty] | ● | ●
T6.1 Bug fixing & polish |  |  | Dec-27, Jan/Feb-28 | [17 empty] | ● | ●
T6.4 MVP launch & handover |  |  | Jan/Feb-28 | [18 empty] | ●
GRAND TOTAL — SALARIES |  |  |  | 2970000
Cloud / GPU Compute | Infrastructure | Direct EGP/mo | — | 630000 | 10925 | 10925 | 18208 | 18208 | 21850 | 21850 | 58266 | 65549 | 65549 | 58266 | 43699 | 36416 | 36416 | 36416 | 40058 | 40058 | 32775 | 14566
QA / UAT Testing & Misc. | Testing & Contingency | Direct EGP/mo | — | 600000 | 15790 | 15790 | 15790 | 15790 | 15790 | 15790 | 15790 | 15790 | 15790 | 15790 | 15790 | 15790 | 15790 | 15790 | 105257 | 105263 | 84210 | 84210
TOTAL PROJECT COST |  |  |  | 4200000
Budget Reconciliation vs. Project Charter
Budget Category |  | Charter Target (EGP) | Charter % | Resource Plan Total (EGP)
Execution Team Salaries (7-person budget) |  | 1890000 | 45% | 1890000
Clinical Advisory Committee (3 full-time) |  | 1080000 | 26% | 1080000
Cloud / GPU Compute |  | 630000 | 15% | 630000
QA / UAT Testing & Misc. |  | 600000 | 14% | 600000
TOTAL PROJECT BUDGET |  | 4200000 | 100% | 4200000
Assumptions & Notes:
1. AI Engineer consolidates ML Engineer, Computer Vision Engineer, VLM/AI Research Engineer, and NLP/LLM Engineer into one AI/ML Development resource.
2. AI Engineer is modelled as 3 specialists at EGP 45,000/month total. The other five tech resources are set at EGP 12,000/month each so the execution-team salary total is exactly EGP 1,890,000 over 18 months, matching the Charter budget target.
3. The Charter has a headcount inconsistency: it states a 7-person tech execution team, while the role description separately lists 3 AI Engineers plus Data Engineer, Full-stack Developer, Mobile Developer, UX/UI Designer, and QA Engineer (8 specialists). The workbook prioritizes the Charter salary total while retaining the 3-AI-specialist role description.
4. Clinical Advisory Committee is modelled as 3 full-time consultants at EGP 20,000/person/month = EGP 1,080,000 over 18 months, matching the Charter.
5. Task months are mapped from the Project Execution Schedule; shared tasks remain under each responsible resource.
6. Cloud/GPU = EGP 630,000 and QA/UAT Testing & Misc. = EGP 600,000, producing the Charter total project budget of EGP 4,200,000.